## 配置任务list
类别 | 项目 | 进度 | 负责人 | step（后置依赖前置） | 备注
玩法-体验整体设计
| 整体玩法框架 & 体验框架设计 | 100% | 斧头 | 1
| 阶段-鱼-钓场-钓具-饵种-饵长度 基本设置表 | 50% | JK | 2 | 改由斧头设计
| 阶段-等级对应 | 80% | 斧头 | 2 | 改由斧头设计
| 兴奋点 元素解锁 错落排布 | 0% | 大宝 | 2 | 改由斧头设计
数值设计
| 各等阶投入-产出表 | 100% | 斧头 | 2
| 各等阶鱼价-竿轮线饵价 | 100% | 斧头 | 2
| 优化各等阶产出-投入表 | 100% | 斧头 | 3
| 鱼价格期望工具表 | 100% | 斧头 | 3
| 鱼长-饵长 工具表 | 0% | 斧头 | 3 | 供JK&斧头主要使用
| Excel跨表单跳转、新建、后退工具 | 100% | 斧头 | 3
| 各阶段鱼种、稀有度、鱼长设计 | 10% | JK | 3
| 各阶段鱼单价设计 | 0% | 斧头 | 3
| 数字美化工具 | 80% | 斧头 | 5
鱼
| 做工具，从设计表→配置表的转换和填入、更新、增加 | 20% | 斧头
| 鱼单价配置 | 0% | 斧头 | 4
| 鱼长度配置 | 0% | 斧头 | 4
| 鱼力量、耐力配置 | 100% | 斧头 | 4
| 鱼力量-代码重构后调整 | 0% | 斧头 | 5
| 结构体习性配置 | 100% | 斧头 | 5
| 觅食水层习性配置 | 100% | 斧头 | 5
| 水温习性配置 | 100% | 斧头 | 5
| 时段习性配置 | 100% | 斧头 | 5
| 饵种习性配置 | 100% | 斧头 | 5
| 饵长度习性 | 100% | 斧头 | 5
| 模拟器检验效果 | 0% | 斧头 | 6
等级配置
| 经验值配置 | 20% | 斧头 | 4
| 赠送货币配置 | 0% | 斧头 | 5
| 赠送物品配置 |  | ？ | 5
| 钓具解锁的升级UI呈现？ |  | 大宝？ | 4
| 经验数据美化 | 0% | 斧头 | 5
搏鱼配置
| 等级-能量配置 | 0% | 斧头 | 4
| 能量-体力配置 | 0% | 斧头 | 4
| 食物-体力配置 | 0% | ？ | 4
任务
| 根据鱼种、关卡设计、系统限制，拉出任务单 | 0% | 大宝 | 2
| 配置通用鱼数量任务 | 0% | 大宝 | 4
| 配置定向鱼数量任务 | 0% | 大宝 | 4
| 配置条件下钓鱼数量任务 | 0% | 大宝 | 4
| 配置饵、钓法钓鱼任务 | 0% | 大宝 | 4
| 配置钓场任务组 | 0% | 大宝 | 4
| 配置任务解锁关系 | 0% | 大宝 | 4
| 难度估算+调整 | 0% | 大宝 | 4
| 奖励配置 | 0% | 大宝 | 4
| 任务多语言处理 | 0% | 大宝 | 4
| 任务关联其他表校验 | 0% | 大宝 | 4
钓场
| 投鱼种类、品质 | 0% | JK？ | 3
| 投鱼权重 | 0% | 斧头 | 4
| 钓场底温 | 0% | 斧头 | 3
| 水流速 | 0% | 浣熊 | 3
| 钓场多语言 | 0% | ？ | 2
| 根据关卡设计，调整地图内结构触发盒 | 0% | 浣熊 | 4
| 在钓场1、2中，为高阶鱼的栖息加特殊结构 | 0% | 浣熊 | 4
| 在钓场1、2中，为传奇鱼的栖息特殊结构加视觉提示 | 0% | 浣熊 | 4
天气
| 钓场1 天气 3条链配置 | 100% | 浣熊 | 2
| 钓场2 天气 3条链配置 | 100% | 浣熊 | 2
| 天气roll权重 配置 | 100% | 浣熊 | 2
| 天气链挂钩钓场 | 100% | 浣熊 | 2
钓具
| 各阶钓具，根据鱼种、关卡作多样化、分野规划 | 0% | JK | 3
| 配置钓具属性 | 0% | JK | 4
| 配置饵长度、感知系数 | 0% | JK | 5
| 配置钓具解锁等级 | 0% | ？ | 4
售卖配置
| 物品售卖批次配置 | 0% | ？ | 4
| 钓具售卖多语言配置 | 0% | ？ | 4
| 钓具售卖等级配置 | 0% | ？ | 4
| 钓具售卖价格配置 | 0% | ？ | 4
| 物品售卖图片配置 | 0% | ？ | 4
| 食物配置 | 0% | ？ | 4
维修
| 维修参数调整 | 0% | 斧头 | 5
| 维修价格调整 | 0% | 斧头 | 5
新手引导
| 新手引导鱼配置 | 0% | 雷子？ | 3
| 新手引导文字速度调整 | 0% | 雷子 | 3
| 新手引导多语言配置 | 0% | 雷子 | 3
成就
| 成就项目列表设计 | 0% | 雷子 | 3
| 成就条件配置 | 0% | 雷子 | 4
| 成就奖励配置 | 0% | 雷子 | 4

## log
TODO
竿降低，饵提高
任务、成就
工具 用中间表和代码 生成饵-姿态-鱼的bp表
回环中抢先尝鲜带来的半数提升，调整框算
维修
调整等级表
饵细化
等级奖励
收益效率改进：钓二阶鱼时夹杂一阶鱼
钓具升级是钓到更好鱼的基础
阶段 | 购置钓具 | 饵总花费 | 钓鱼累积xp | 本阶段任务总gold | 本阶段任务总xp | 维修总花费
1 | 32000 | 640 | 14400 | 9600 | 19200 | 0
2 | 96000 | 1920 | 43200 | 28800 | 57600 | 800
3 | 288000 | 5760 | 129600 | 86400 | 172800 | 4800
4 | 1296000 | 17280 | 583200 | 388800 | 777600 | 21600
5 | 3888000 | 51840 | 1749600 | 1166400 | 2332800 | 86400
6 | 11664000 | 155520 | 5248800 | 3499200 | 6998400 | 324000
7 | 34992000 | 466560 | 15746400 | 10497600 | 20995200 | 1166400
| 32000 | 640 | 14000 | 9600 | 19000 | 0
| 96000 | 1900 | 43000 | 29000 | 58000 | 800
| 290000 | 5800 | 130000 | 86000 | 170000 | 4800
| 1300000 | 17000 | 580000 | 390000 | 780000 | 22000
| 3900000 | 52000 | 1700000 | 1200000 | 2300000 | 86000
| 12000000 | 160000 | 5200000 | 3500000 | 7000000 | 320000
| 35000000 | 470000 | 16000000 | 10000000 | 21000000 | 1200000

## 鱼单价工具
填写绿色格子，勿动白色、蓝色单元格！ |  |  |  |  | cm | cm | g | g |  |  |  |  | 主要用于同鱼种的加权 |  | 这个鱼种多个品质加权 | (/minute) |  | 这个鱼种多个品质加权
等阶 | 中文名 | 鱼种 | 稀有度 | 钓场 | 最小长度 | 最大长度 | 最小重量 | 最大重量 | 期望重量 | 重量参数a | 重量参数b | 单价 | 权重 | 期望价格/条 | 本阶段期望gold/条 | 钓鱼时间 | 提供单位时间收益 | 本阶段期望gold/分钟 | xp | min_reward | 行标签 | 求和项:单价
[21 empty] | Black_Crappie | 7750
3 | 丁鱥 | Tench | _Common | 1 | 28 | 46 | 270.0096 | 1197.2328 | 659.895 | 0.0123 | 3 | 799 | 378 | 527 | 3704 | 0.5 | 7408 | 7408 | 1038 | 215 | Bluegill_Sunfish | 3000
3 | 丁鱥 | Tench | _Trophy | 1 | 46 | 60 | 1197.2328 | 2656.8 | 1863.1302 | 0.0123 | 3 | 2000 | 189 | 3726 | 3704 | 0.5 | 7408 | 7408 | 2600 | 2394 | Bowfin | 750
3 | 丁鱥 | Tench | _Unique | 1 | 60 | 70 | 2656.8 | 4218.9 | 3397.875 | 0.0123 | 3 | 3000 | 94 | 10193 | 3704 | 0.5 | 7408 | 7408 | 3900 | 7970 | Buffalofish | 750
3 | 丁鱥 | Tench | _Apex | 1 | 70 | 77 | 4218.9 | 5615.3559 | 4894.9787 | 0.0123 | 3 | 4000 | 37 | 19579 | 3704 | 0.5 | 7408 | 7408 | 5200 | 16875 | Channel_Catfish | 2500
4 | 金体美鳊 | Golden_Bream | _Common | 1 | 12 | 20 | 28.5262 | 138.2791 | 74.0608 | 0.0132 | 3.09 | 7000 | 378 | 518 | 1651 | 0.5 | 3302 | 3302 | 9100 | 199 | Golden_Bream | 37250
4 | 金体美鳊 | Golden_Bream | _Trophy | 1 | 20 | 26 | 138.2791 | 311.0581 | 216.8675 | 0.0132 | 3.09 | 8000 | 189 | 1734 | 1651 | 0.5 | 3302 | 3302 | 10400 | 1106 | Green_Sunfish | 11000
4 | 金体美鳊 | Golden_Bream | _Unique | 1 | 26 | 30 | 311.0581 | 484.0371 | 393.2518 | 0.0132 | 3.09 | 10250 | 94 | 4030 | 1651 | 0.5 | 3302 | 3302 | 13325 | 3188 | Largemouth_Bass | 3250
4 | 金体美鳊 | Golden_Bream | _Apex | 1 | 30 | 33 | 484.0371 | 649.8034 | 564.1729 | 0.0132 | 3.09 | 12000 | 37 | 6770 | 1651 | 0.5 | 3302 | 3302 | 15600 | 5808 | Muskellunge | 500
3 | 绿太阳鱼 | Green_Sunfish | _Common | 1 | 12 | 20 | 20.736 | 96 | 52.224 | 0.012 | 3 | 3000 | 857 | 156 | 417 | 0.6 | 695 | 695 | 3900 | 62 | Pumpkinseed_Sunfish | 2000
3 | 绿太阳鱼 | Green_Sunfish | _Trophy | 1 | 20 | 26 | 96 | 210.912 | 148.488 | 0.012 | 3 | 3750 | 428 | 556 | 417 | 0.6 | 695 | 695 | 4875 | 360 | Redear_Sunfish | 500
3 | 绿太阳鱼 | Green_Sunfish | _Unique | 1 | 26 | 31 | 210.912 | 357.492 | 279.927 | 0.012 | 3 | 4250 | 214 | 1189 | 417 | 0.6 | 695 | 695 | 5525 | 896 | Redspotted_Sunfish | 17500
2 | 黑斑刺盖太阳鱼 | Black_Crappie | _Young | 1 | 12 | 20 | 21.2683 | 103.6249 | 55.4048 | 0.0096 | 3.1 | 1000 | 500 | 55 | 212 | 0.6 | 353 | 191 | 1300 | 21 | Rock_Bass | 6000
2 | 黑斑刺盖太阳鱼 | Black_Crappie | _Common | 1 | 20 | 32 | 103.6249 | 444.8731 | 247.2244 | 0.0096 | 3.1 | 1500 | 500 | 370 | 212 | 0.6 | 353 | 191 | 1950 | 155 | Striped_Bass | 1250
2 | 白斑刺盖太阳鱼 | White_Crappie | _Young | 1 | 13 | 21 | 25.776 | 106.589 | 60.0783 | 0.013 | 2.96 | 1250 | 500 | 75 | 255 | 0.6 | 425 | 425 | 1625 | 32 | Tench | 9799
2 | 白斑刺盖太阳鱼 | White_Crappie | _Common | 1 | 21 | 34 | 106.589 | 443.7322 | 249.5829 | 0.013 | 2.96 | 1750 | 500 | 436 | 255 | 0.6 | 425 | 425 | 2275 | 186 | Walleye | 750
2 | 红斑太阳鱼 | Redspotted_Sunfish | _Young | 1 | 10 | 12 | 12.3561 | 21.4294 | 16.6158 | 0.0118 | 3.02 | 7500 | 500 | 124 | 216 | 0.6 | 360 | 360 | 9750 | 92 | White_Channel_Catfish | 1750
2 | 红斑太阳鱼 | Redspotted_Sunfish | _Common | 1 | 12 | 15 | 21.4294 | 42.0414 | 30.9676 | 0.0118 | 3.02 | 10000 | 500 | 309 | 216 | 0.6 | 360 | 360 | 13000 | 214 | White_Crappie | 3000
2 | 大口黑鲈 | Largemouth_Bass | _Young | 1 | 19 | 30 | 72.9068 | 318.7832 | 175.7633 | 0.0054 | 3.23 | 1000 | 500 | 175 | 502 | 0.6 | 836 | 432 | 1300 | 72 | Yellow_Perch | 7250
2 | 大口黑鲈 | Largemouth_Bass | _Common | 1 | 30 | 49 | 318.7832 | 1554.9882 | 829.0522 | 0.0054 | 3.23 | 1000 | 500 | 829 | 502 | 0.6 | 836 | 432 | 1300 | 318 | (空白)
2 | 斑点叉尾鮰 | Channel_Catfish | _Young | 1 | 33 | 53 | 427.6253 | 1866.3065 | 1031.6619 | 0.0081 | 3.11 | 1000 | 500 | 1031 | 2817 | 0.6 | 4695 | 2382 | 1300 | 427 | 总计 | 116549
2 | 斑点叉尾鮰 | Channel_Catfish | _Common | 1 | 53 | 86 | 1866.3065 | 8409.5973 | 4603.046 | 0.0081 | 3.11 | 1000 | 500 | 4603 | 2817 | 0.6 | 4695 | 2382 | 1300 | 1866
1 | 驼背太阳鱼 | Pumpkinseed_Sunfish | _Young | 1 | 10 | 16 | 11.758 | 46.8216 | 26.716 | 0.0135 | 2.94 | 1000 | 500 | 26 | 63 | 0.6 | 105 | 105 | 1300 | 11
1 | 驼背太阳鱼 | Pumpkinseed_Sunfish | _Common | 1 | 16 | 25 | 46.8216 | 173.8911 | 101.4702 | 0.0135 | 2.94 | 1000 | 500 | 101 | 63 | 0.6 | 105 | 105 | 1300 | 46
3 | 水牛鱼 | Buffalofish | _Young | 1 | 30 | 48 | 409.6659 | 1717.8916 | 962.5352 | 0.0128 | 3.05 | 250 | 500 | 240 | 1162 | 0.6 | 1936 | 1936 | 325 | 102
3 | 水牛鱼 | Buffalofish | _Common | 1 | 48 | 78 | 1717.8916 | 7552.6352 | 4169.9321 | 0.0128 | 3.05 | 500 | 500 | 2084 | 1162 | 0.6 | 1936 | 1936 | 650 | 858
1 | 小冠太阳鱼 | Redear_Sunfish | _Young | 1 | 10 | 16 | 15.9743 | 68.9025 | 38.2278 | 0.0124 | 3.11 | 225 | 500 | 8 | 27 | 0.6 | 45 | 45 | 292 | 3
1 | 小冠太阳鱼 | Redear_Sunfish | _Common | 1 | 16 | 26 | 68.9025 | 311.8809 | 170.4736 | 0.0124 | 3.11 | 275 | 500 | 46 | 27 | 0.6 | 45 | 45 | 357 | 18
1 | 蓝鳃太阳鱼 | Bluegill_Sunfish | _Young | 1 | 10 | 16 | 14.7435 | 65.1057 | 35.8276 | 0.0102 | 3.16 | 1250 | 500 | 44 | 177 | 0.6 | 295 | 295 | 1625 | 18
1 | 蓝鳃太阳鱼 | Bluegill_Sunfish | _Common | 1 | 16 | 27 | 65.1057 | 340.1807 | 177.9543 | 0.0102 | 3.16 | 1750 | 500 | 311 | 177 | 0.6 | 295 | 295 | 2275 | 113
5 | 白化叉尾鮰 | White_Channel_Catfish | _Common | 2 | 53 | 86 | 1866.3065 | 8409.5973 | 4603.046 | 0.0081 | 3.11 | 250 | 540 | 1150 | 4720 | 0.6 | 7866 | 7866 | 325 | 466
5 | 白化叉尾鮰 | White_Channel_Catfish | _Trophy | 2 | 86 | 112 | 8409.5973 | 19122.8699 | 13274.7151 | 0.0081 | 3.11 | 250 | 270 | 3318 | 4720 | 0.6 | 7866 | 7866 | 325 | 2102
5 | 白化叉尾鮰 | White_Channel_Catfish | _Unique | 2 | 112 | 132 | 19122.8699 | 31876.4497 | 25132.9676 | 0.0081 | 3.11 | 500 | 135 | 12566 | 4720 | 0.6 | 7866 | 7866 | 650 | 9561
5 | 白化叉尾鮰 | White_Channel_Catfish | _Apex | 2 | 132 | 145 | 31876.4497 | 42691.3124 | 37105.5388 | 0.0081 | 3.11 | 750 | 54 | 27829 | 4720 | 0.6 | 7866 | 7866 | 975 | 23907
5 | 美洲条纹狼鲈 | Striped_Bass | _Common | 2 | 40 | 65 | 1384.3551 | 6805.2884 | 3616.5378 | 0.0077 | 3.28 | 250 | 378 | 904 | 2849 | 0.6 | 4748 | 4590 | 325 | 346
5 | 美洲条纹狼鲈 | Striped_Bass | _Trophy | 2 | 65 | 85 | 6805.2884 | 16405.3236 | 11122.7659 | 0.0077 | 3.28 | 250 | 189 | 2780 | 2849 | 0.6 | 4748 | 4590 | 325 | 1701
5 | 美洲条纹狼鲈 | Striped_Bass | _Unique | 2 | 85 | 100 | 16405.3236 | 27957.0102 | 21826.3009 | 0.0077 | 3.28 | 250 | 94 | 5456 | 2849 | 0.6 | 4748 | 4590 | 325 | 4101
5 | 美洲条纹狼鲈 | Striped_Bass | _Apex | 2 | 100 | 110 | 27957.0102 | 38217.1883 | 32901.6284 | 0.0077 | 3.28 | 500 | 37 | 16450 | 2849 | 1.6 | 1780 | 4590 | 650 | 13978
4 | 玻璃梭鲈 | Walleye | _Common | 2 | 43 | 70 | 1119.4689 | 5508.594 | 2927.0919 | 0.0051 | 3.27 | 250 | 800 | 731 | 1668 | 2.6 | 641 | 550 | 325 | 279
4 | 玻璃梭鲈 | Walleye | _Trophy | 2 | 70 | 91 | 5508.594 | 12990.789 | 8883.241 | 0.0051 | 3.27 | 250 | 400 | 2220 | 1668 | 3.6 | 463 | 550 | 325 | 1377
4 | 玻璃梭鲈 | Walleye | _Unique | 2 | 91 | 107 | 12990.789 | 22062.5206 | 17250.1158 | 0.0051 | 3.27 | 250 | 200 | 4312 | 1668 | 4.6 | 362 | 550 | 325 | 3247
3 | 北美狗鱼 | Muskellunge | _Young | 2 | 38 | 60 | 882.4215 | 3965.5702 | 2165.7363 | 0.0056 | 3.29 | 250 | 500 | 541 | 1585 | 5.6 | 283 | 261 | 325 | 220
3 | 北美狗鱼 | Muskellunge | _Common | 2 | 60 | 98 | 3965.5702 | 19921.4899 | 10516.3281 | 0.0056 | 3.29 | 250 | 500 | 2629 | 1585 | 6.6 | 240 | 261 | 325 | 991
2 | 弓鳍鱼 | Bowfin | _Young | 2 | 22 | 35 | 154.3392 | 707.7388 | 384.1732 | 0.0061 | 3.28 | 250 | 500 | 96 | 512 | 7.6 | 67 | 63 | 325 | 38
2 | 弓鳍鱼 | Bowfin | _Common | 2 | 35 | 57 | 707.7388 | 3504.2845 | 1858.2557 | 0.0061 | 3.28 | 500 | 500 | 929 | 512 | 8.6 | 59 | 63 | 650 | 353
2 | 斑点叉尾鮰 | Channel_Catfish | _Young | 2 | 33 | 53 | 427.6253 | 1866.3065 | 1031.6619 | 0.0081 | 3.11 | 250 | 500 | 257 | 703 | 9.6 | 73 | 2382 | 325 | 106
2 | 斑点叉尾鮰 | Channel_Catfish | _Common | 2 | 53 | 86 | 1866.3065 | 8409.5973 | 4603.046 | 0.0081 | 3.11 | 250 | 500 | 1150 | 703 | 10.6 | 66 | 2382 | 325 | 466
2 | 大口黑鲈 | Largemouth_Bass | _Young | 2 | 19 | 30 | 72.9068 | 318.7832 | 175.7633 | 0.0054 | 3.23 | 500 | 500 | 87 | 354 | 11.6 | 30 | 432 | 650 | 36
2 | 大口黑鲈 | Largemouth_Bass | _Common | 2 | 30 | 49 | 318.7832 | 1554.9882 | 829.0522 | 0.0054 | 3.23 | 750 | 500 | 621 | 354 | 12.6 | 28 | 432 | 975 | 239
2 | 黑斑刺盖太阳鱼 | Black_Crappie | _Young | 2 | 12 | 20 | 21.2683 | 103.6249 | 55.4048 | 0.0096 | 3.1 | 2250 | 500 | 124 | 432 | 13.6 | 31 | 191 | 2925 | 47
2 | 黑斑刺盖太阳鱼 | Black_Crappie | _Common | 2 | 20 | 32 | 103.6249 | 444.8731 | 247.2244 | 0.0096 | 3.1 | 3000 | 500 | 741 | 432 | 14.6 | 29 | 191 | 3900 | 310
2 | 黄鲈 | Yellow_Perch | _Young | 2 | 10 | 16 | 13.7286 | 62.9471 | 34.1929 | 0.0079 | 3.24 | 3250 | 500 | 111 | 380 | 15.6 | 24 | 23 | 4225 | 44
2 | 黄鲈 | Yellow_Perch | _Common | 2 | 16 | 26 | 62.9471 | 303.4875 | 162.3472 | 0.0079 | 3.24 | 4000 | 500 | 649 | 380 | 16.6 | 22 | 23 | 5200 | 251
2 | 岩钝鲈 | Rock_Bass | _Young | 2 | 10 | 18 | 12.5 | 72.9 | 37.1 | 0.0125 | 3 | 2750 | 500 | 102 | 349 | 17.6 | 19 | 18 | 3575 | 34
2 | 岩钝鲈 | Rock_Bass | _Common | 2 | 18 | 30 | 72.9 | 337.5 | 183.6 | 0.0125 | 3 | 3250 | 500 | 596 | 349 | 18.6 | 18 | 18 | 4225 | 236

## Sheet1
填写绿色格子，勿动白色、蓝色单元格！ |  |  |  |  | cm | cm | g | g |  |  |  |  | 主要用于同鱼种的加权
等阶 | 中文名 | 鱼种 | 稀有度 | 钓场 | 最小长度 | 最大长度 | 最小重量 | 最大重量 | 期望重量 | 重量参数a | 重量参数b | 单价 | 权重 | 期望价格/条 | 单条*权重
[16 empty] | 行标签 | 求和项:单条*权重 | 求和项:权重
3 | 丁鱥 | Tench | _Common | 1 | 28 | 46 | 270.0096 | 1197.2328 | 659.895 | 0.0123 | 3 | 799 | 378 | 527 | 199206 | 1 | 9798431 | 11895
3 | 丁鱥 | Tench | _Trophy | 1 | 46 | 60 | 1197.2328 | 2656.8 | 1863.1302 | 0.0123 | 3 | 2000 | 189 | 3726 | 704214 | Black_Crappie | 212500 | 1000
3 | 丁鱥 | Tench | _Unique | 1 | 60 | 70 | 2656.8 | 4218.9 | 3397.875 | 0.0123 | 3 | 3000 | 94 | 10193 | 958142 | Bluegill_Sunfish | 177500 | 1000
3 | 丁鱥 | Tench | _Apex | 1 | 70 | 77 | 4218.9 | 5615.3559 | 4894.9787 | 0.0123 | 3 | 4000 | 37 | 19579 | 724423 | Buffalofish | 1162000 | 1000
4 | 金体美鳊 | Golden_Bream | _Common | 1 | 12 | 20 | 28.5262 | 138.2791 | 74.0608 | 0.0132 | 3.09 | 7000 | 378 | 518 | 195804 | Channel_Catfish | 2817000 | 1000
4 | 金体美鳊 | Golden_Bream | _Trophy | 1 | 20 | 26 | 138.2791 | 311.0581 | 216.8675 | 0.0132 | 3.09 | 8000 | 189 | 1734 | 327726 | Golden_Bream | 1152840 | 698
4 | 金体美鳊 | Golden_Bream | _Unique | 1 | 26 | 30 | 311.0581 | 484.0371 | 393.2518 | 0.0132 | 3.09 | 10250 | 94 | 4030 | 378820 | Green_Sunfish | 626106 | 1499
4 | 金体美鳊 | Golden_Bream | _Apex | 1 | 30 | 33 | 484.0371 | 649.8034 | 564.1729 | 0.0132 | 3.09 | 12000 | 37 | 6770 | 250490 | Largemouth_Bass | 502000 | 1000
3 | 绿太阳鱼 | Green_Sunfish | _Common | 1 | 12 | 20 | 20.736 | 96 | 52.224 | 0.012 | 3 | 3000 | 857 | 156 | 133692 | Pumpkinseed_Sunfish | 63500 | 1000
3 | 绿太阳鱼 | Green_Sunfish | _Trophy | 1 | 20 | 26 | 96 | 210.912 | 148.488 | 0.012 | 3 | 3750 | 428 | 556 | 237968 | Redear_Sunfish | 27000 | 1000
3 | 绿太阳鱼 | Green_Sunfish | _Unique | 1 | 26 | 31 | 210.912 | 357.492 | 279.927 | 0.012 | 3 | 4250 | 214 | 1189 | 254446 | Redspotted_Sunfish | 216500 | 1000
2 | 黑斑刺盖太阳鱼 | Black_Crappie | _Young | 1 | 12 | 20 | 21.2683 | 103.6249 | 55.4048 | 0.0096 | 3.1 | 1000 | 500 | 55 | 27500 | Tench | 2585985 | 698
2 | 黑斑刺盖太阳鱼 | Black_Crappie | _Common | 1 | 20 | 32 | 103.6249 | 444.8731 | 247.2244 | 0.0096 | 3.1 | 1500 | 500 | 370 | 185000 | White_Crappie | 255500 | 1000
2 | 白斑刺盖太阳鱼 | White_Crappie | _Young | 1 | 13 | 21 | 25.776 | 106.589 | 60.0783 | 0.013 | 2.96 | 1250 | 500 | 75 | 37500 | 2 | 13356382 | 10097
2 | 白斑刺盖太阳鱼 | White_Crappie | _Common | 1 | 21 | 34 | 106.589 | 443.7322 | 249.5829 | 0.013 | 2.96 | 1750 | 500 | 436 | 218000 | Black_Crappie | 432500 | 1000
2 | 红斑太阳鱼 | Redspotted_Sunfish | _Young | 1 | 10 | 12 | 12.3561 | 21.4294 | 16.6158 | 0.0118 | 3.02 | 7500 | 500 | 124 | 62000 | Bowfin | 512500 | 1000
2 | 红斑太阳鱼 | Redspotted_Sunfish | _Common | 1 | 12 | 15 | 21.4294 | 42.0414 | 30.9676 | 0.0118 | 3.02 | 10000 | 500 | 309 | 154500 | Channel_Catfish | 703500 | 1000
2 | 大口黑鲈 | Largemouth_Bass | _Young | 1 | 19 | 30 | 72.9068 | 318.7832 | 175.7633 | 0.0054 | 3.23 | 1000 | 500 | 175 | 87500 | Largemouth_Bass | 354000 | 1000
2 | 大口黑鲈 | Largemouth_Bass | _Common | 1 | 30 | 49 | 318.7832 | 1554.9882 | 829.0522 | 0.0054 | 3.23 | 1000 | 500 | 829 | 414500 | Muskellunge | 1585000 | 1000
2 | 斑点叉尾鮰 | Channel_Catfish | _Young | 1 | 33 | 53 | 427.6253 | 1866.3065 | 1031.6619 | 0.0081 | 3.11 | 1000 | 500 | 1031 | 515500 | Rock_Bass | 349000 | 1000
2 | 斑点叉尾鮰 | Channel_Catfish | _Common | 1 | 53 | 86 | 1866.3065 | 8409.5973 | 4603.046 | 0.0081 | 3.11 | 1000 | 500 | 4603 | 2301500 | Striped_Bass | 1988646 | 698
1 | 驼背太阳鱼 | Pumpkinseed_Sunfish | _Young | 1 | 10 | 16 | 11.758 | 46.8216 | 26.716 | 0.0135 | 2.94 | 1000 | 500 | 26 | 13000 | Walleye | 2335200 | 1400
1 | 驼背太阳鱼 | Pumpkinseed_Sunfish | _Common | 1 | 16 | 25 | 46.8216 | 173.8911 | 101.4702 | 0.0135 | 2.94 | 1000 | 500 | 101 | 50500 | White_Channel_Catfish | 4716036 | 999
3 | 水牛鱼 | Buffalofish | _Young | 1 | 30 | 48 | 409.6659 | 1717.8916 | 962.5352 | 0.0128 | 3.05 | 250 | 500 | 240 | 120000 | Yellow_Perch | 380000 | 1000
3 | 水牛鱼 | Buffalofish | _Common | 1 | 48 | 78 | 1717.8916 | 7552.6352 | 4169.9321 | 0.0128 | 3.05 | 500 | 500 | 2084 | 1042000 | 总计 | 23154813 | 21992
1 | 小冠太阳鱼 | Redear_Sunfish | _Young | 1 | 10 | 16 | 15.9743 | 68.9025 | 38.2278 | 0.0124 | 3.11 | 225 | 500 | 8 | 4000
1 | 小冠太阳鱼 | Redear_Sunfish | _Common | 1 | 16 | 26 | 68.9025 | 311.8809 | 170.4736 | 0.0124 | 3.11 | 275 | 500 | 46 | 23000
1 | 蓝鳃太阳鱼 | Bluegill_Sunfish | _Young | 1 | 10 | 16 | 14.7435 | 65.1057 | 35.8276 | 0.0102 | 3.16 | 1250 | 500 | 44 | 22000
1 | 蓝鳃太阳鱼 | Bluegill_Sunfish | _Common | 1 | 16 | 27 | 65.1057 | 340.1807 | 177.9543 | 0.0102 | 3.16 | 1750 | 500 | 311 | 155500
5 | 白化叉尾鮰 | White_Channel_Catfish | _Common | 2 | 53 | 86 | 1866.3065 | 8409.5973 | 4603.046 | 0.0081 | 3.11 | 250 | 540 | 1150 | 621000
5 | 白化叉尾鮰 | White_Channel_Catfish | _Trophy | 2 | 86 | 112 | 8409.5973 | 19122.8699 | 13274.7151 | 0.0081 | 3.11 | 250 | 270 | 3318 | 895860
5 | 白化叉尾鮰 | White_Channel_Catfish | _Unique | 2 | 112 | 132 | 19122.8699 | 31876.4497 | 25132.9676 | 0.0081 | 3.11 | 500 | 135 | 12566 | 1696410
5 | 白化叉尾鮰 | White_Channel_Catfish | _Apex | 2 | 132 | 145 | 31876.4497 | 42691.3124 | 37105.5388 | 0.0081 | 3.11 | 750 | 54 | 27829 | 1502766
5 | 美洲条纹狼鲈 | Striped_Bass | _Common | 2 | 40 | 65 | 1384.3551 | 6805.2884 | 3616.5378 | 0.0077 | 3.28 | 250 | 378 | 904 | 341712
5 | 美洲条纹狼鲈 | Striped_Bass | _Trophy | 2 | 65 | 85 | 6805.2884 | 16405.3236 | 11122.7659 | 0.0077 | 3.28 | 250 | 189 | 2780 | 525420
5 | 美洲条纹狼鲈 | Striped_Bass | _Unique | 2 | 85 | 100 | 16405.3236 | 27957.0102 | 21826.3009 | 0.0077 | 3.28 | 250 | 94 | 5456 | 512864
5 | 美洲条纹狼鲈 | Striped_Bass | _Apex | 2 | 100 | 110 | 27957.0102 | 38217.1883 | 32901.6284 | 0.0077 | 3.28 | 500 | 37 | 16450 | 608650
4 | 玻璃梭鲈 | Walleye | _Common | 2 | 43 | 70 | 1119.4689 | 5508.594 | 2927.0919 | 0.0051 | 3.27 | 250 | 800 | 731 | 584800
4 | 玻璃梭鲈 | Walleye | _Trophy | 2 | 70 | 91 | 5508.594 | 12990.789 | 8883.241 | 0.0051 | 3.27 | 250 | 400 | 2220 | 888000
4 | 玻璃梭鲈 | Walleye | _Unique | 2 | 91 | 107 | 12990.789 | 22062.5206 | 17250.1158 | 0.0051 | 3.27 | 250 | 200 | 4312 | 862400
3 | 北美狗鱼 | Muskellunge | _Young | 2 | 38 | 60 | 882.4215 | 3965.5702 | 2165.7363 | 0.0056 | 3.29 | 250 | 500 | 541 | 270500
3 | 北美狗鱼 | Muskellunge | _Common | 2 | 60 | 98 | 3965.5702 | 19921.4899 | 10516.3281 | 0.0056 | 3.29 | 250 | 500 | 2629 | 1314500
2 | 弓鳍鱼 | Bowfin | _Young | 2 | 22 | 35 | 154.3392 | 707.7388 | 384.1732 | 0.0061 | 3.28 | 250 | 500 | 96 | 48000
2 | 弓鳍鱼 | Bowfin | _Common | 2 | 35 | 57 | 707.7388 | 3504.2845 | 1858.2557 | 0.0061 | 3.28 | 500 | 500 | 929 | 464500
2 | 斑点叉尾鮰 | Channel_Catfish | _Young | 2 | 33 | 53 | 427.6253 | 1866.3065 | 1031.6619 | 0.0081 | 3.11 | 250 | 500 | 257 | 128500
2 | 斑点叉尾鮰 | Channel_Catfish | _Common | 2 | 53 | 86 | 1866.3065 | 8409.5973 | 4603.046 | 0.0081 | 3.11 | 250 | 500 | 1150 | 575000
2 | 大口黑鲈 | Largemouth_Bass | _Young | 2 | 19 | 30 | 72.9068 | 318.7832 | 175.7633 | 0.0054 | 3.23 | 500 | 500 | 87 | 43500
2 | 大口黑鲈 | Largemouth_Bass | _Common | 2 | 30 | 49 | 318.7832 | 1554.9882 | 829.0522 | 0.0054 | 3.23 | 750 | 500 | 621 | 310500
2 | 黑斑刺盖太阳鱼 | Black_Crappie | _Young | 2 | 12 | 20 | 21.2683 | 103.6249 | 55.4048 | 0.0096 | 3.1 | 2250 | 500 | 124 | 62000
2 | 黑斑刺盖太阳鱼 | Black_Crappie | _Common | 2 | 20 | 32 | 103.6249 | 444.8731 | 247.2244 | 0.0096 | 3.1 | 3000 | 500 | 741 | 370500
2 | 黄鲈 | Yellow_Perch | _Young | 2 | 10 | 16 | 13.7286 | 62.9471 | 34.1929 | 0.0079 | 3.24 | 3250 | 500 | 111 | 55500
2 | 黄鲈 | Yellow_Perch | _Common | 2 | 16 | 26 | 62.9471 | 303.4875 | 162.3472 | 0.0079 | 3.24 | 4000 | 500 | 649 | 324500
2 | 岩钝鲈 | Rock_Bass | _Young | 2 | 10 | 18 | 12.5 | 72.9 | 37.1 | 0.0125 | 3 | 2750 | 500 | 102 | 51000
2 | 岩钝鲈 | Rock_Bass | _Common | 2 | 18 | 30 | 72.9 | 337.5 | 183.6 | 0.0125 | 3 | 3250 | 500 | 596 | 298000

## 鱼种重量参数
手调鱼种string | 鱼种string | 鱼种类 | STRING | 重量参数a | 重量参数b
Redear_Sunfish | Redear_Sunfish | Redear Sunfish | 小冠太阳鱼 | 0.0124 | 3.11
Buffalofish | Buffalo | Buffalo | 水牛鱼 | 0.0128 | 3.05
Bowfin | Bowfin | Bowfin | 弓鳍鱼 | 0.0061 | 3.28
Yellow_Perch | Yellow_Perch | Yellow Perch | 黄鲈 | 0.0079 | 3.24
Channel_Catfish | Channel_Catfish | Channel Catfish | 斑点叉尾鮰 | 0.0081 | 3.11
Muskellunge | Muskellunge | Muskellunge | 北美狗鱼 | 0.0056 | 3.29
Alewife | Alewife | Alewife | 灰西鲱 | 0.0054 | 3.14
Striped_Bass | Striped_Bass | Striped Bass | 美洲条纹狼鲈 | 0.0077 | 3.28
Blacktail_Shiner | Blacktail_Shiner | Blacktail Shiner | 黑尾沙丁鱼 | 0.0072 | 3.2
Brook_Trout | Brook_Trout | Brook Trout | 美洲红点鲑 | 0.0101 | 3.01
Tench | Tench | Tench | 丁鱥 | 0.0123 | 3
Freshwater_Drum | Freshwater_Drum | Freshwater Drum | 淡水石首鱼 | 0.0085 | 3.12
Largemouth_Bass | Largemouth_Bass | Largemouth Bass | 大口黑鲈 | 0.0054 | 3.23
Spotted_Bass | Spotted_Bass | Spotted Bass | 斑点黑鲈 | 0.006 | 3.22
White_Crappie | White_Crappie | White Crappie | 白斑刺盖太阳鱼 | 0.013 | 2.96
Rock_Bass | Rock_Bass | Rock Bass | 岩钝鲈 | 0.0125 | 3
Smallmouth_Bass | Smallmouth_Bass | Smallmouth Bass | 小口黑鲈 | 0.0052 | 3.23
Black_Crappie | Black_Crappie | Black Crappie | 黑斑刺盖太阳鱼 | 0.0096 | 3.1
Pumpkinseed_Sunfish | Pumpkinseed_Sunfish | Pumpkinseed Sunfish | 驼背太阳鱼 | 0.0135 | 2.94
Green_Sunfish | Green_Sunfish | Green Sunfish | 绿太阳鱼 | 0.012 | 3
Redspotted_Sunfish | Redspotted_Sunfish | Redspotted Sunfish | 红斑太阳鱼 | 0.0118 | 3.02
Chain_Pickerel | Chain_Pickerel | Chain Pickerel | 链纹狗鱼 | 0.0057 | 3.27
Sauger | Sauger | Sauger | 加拿大梭鲈 | 0.0048 | 3.32
Walleye | Walleye | Walleye | 玻璃梭鲈 | 0.0051 | 3.27
Rainbow_Trout | Rainbow_Trout | Rainbow Trout | 虹鳟 | 0.01 | 3
Golden_Trout | Golden_Trout | Golden Trout | 金鳟 | 0.0098 | 3.02
Bluegill_Sunfish | Bluegill_Sunfish | Bluegill Sunfish | 蓝鳃太阳鱼 | 0.0102 | 3.16
American_Eel | American_Eel | American Eel | 美洲鳗鲡 | 0.0009 | 3.49
Bream | Bream | Bream | 美鳊 | 0.0128 | 3.11
Golden_Bream | Golden_Bream | Golden Bream | 金体美鳊 | 0.0132 | 3.09
Longback_Dace | Longback_Dace | Longback Dace | 长背亚口鱼 | 0.008 | 3.2
White_Channel_Catfish | White_Channel_Catfish | White Channel Catfish | 白化叉尾鮰 | 0.0081 | 3.11

## 饵长-鱼长工具
填写绿色格子，勿动白色、蓝色单元格！ |  |  |  | cm | cm
阶段 | 中文名 | 鱼种 | 稀有度 | 最小长度 | 最大长度
3 | 丁鱥 | Tench | _Common | 28 | 46
3 | 丁鱥 | Tench | _Trophy | 46 | 60
3 | 丁鱥 | Tench | _Unique | 60 | 70
3 | 丁鱥 | Tench | _Apex | 70 | 77
4 | 金体美鳊 | Golden_Bream | _Common | 12 | 20
4 | 金体美鳊 | Golden_Bream | _Trophy | 20 | 26
4 | 金体美鳊 | Golden_Bream | _Unique | 26 | 30
4 | 金体美鳊 | Golden_Bream | _Apex | 30 | 33
3 | 绿太阳鱼 | Green_Sunfish | _Common | 12 | 20
3 | 绿太阳鱼 | Green_Sunfish | _Trophy | 20 | 26
3 | 绿太阳鱼 | Green_Sunfish | _Unique | 26 | 31
2 | 黑斑刺盖太阳鱼 | Black_Crappie | _Young | 12 | 20
2 | 黑斑刺盖太阳鱼 | Black_Crappie | _Common | 20 | 32
2 | 白斑刺盖太阳鱼 | White_Crappie | _Young | 13 | 21
2 | 白斑刺盖太阳鱼 | White_Crappie | _Common | 21 | 34
2 | 红斑太阳鱼 | Redspotted_Sunfish | _Young | 10 | 12
2 | 红斑太阳鱼 | Redspotted_Sunfish | _Common | 12 | 15
2 | 大口黑鲈 | Largemouth_Bass | _Young | 19 | 30
2 | 大口黑鲈 | Largemouth_Bass | _Common | 30 | 49
2 | 斑点叉尾鮰 | Channel_Catfish | _Young | 33 | 53
2 | 斑点叉尾鮰 | Channel_Catfish | _Common | 53 | 86
1 | 驼背太阳鱼 | Pumpkinseed_Sunfish | _Young | 10 | 16
1 | 驼背太阳鱼 | Pumpkinseed_Sunfish | _Common | 16 | 25
3 | 水牛鱼 | Buffalofish | _Young | 30 | 48
3 | 水牛鱼 | Buffalofish | _Common | 48 | 78
1 | 小冠太阳鱼 | Redear_Sunfish | _Young | 10 | 16
1 | 小冠太阳鱼 | Redear_Sunfish | _Common | 16 | 26
1 | 蓝鳃太阳鱼 | Bluegill_Sunfish | _Young | 10 | 16
1 | 蓝鳃太阳鱼 | Bluegill_Sunfish | _Common | 16 | 27
5 | 白化叉尾鮰 | White_Channel_Catfish | _Common | 53 | 86
5 | 白化叉尾鮰 | White_Channel_Catfish | _Trophy | 86 | 112
5 | 白化叉尾鮰 | White_Channel_Catfish | _Unique | 112 | 132
5 | 白化叉尾鮰 | White_Channel_Catfish | _Apex | 132 | 145
5 | 美洲条纹狼鲈 | Striped_Bass | _Common | 40 | 65
5 | 美洲条纹狼鲈 | Striped_Bass | _Trophy | 65 | 85
5 | 美洲条纹狼鲈 | Striped_Bass | _Unique | 85 | 100

## 数据透视表
值
阶段 | 求和项:任务经验 | 求和项:任务金币 | 求和项:经验目标
coeff |  | 0.3 | 1.3
1 | 0 | 0 | 0
2 | 0 | 0 | 0
3 | 0 | 0 | 0
4 | 0 | 0 | 0
5 | 0 | 0 | 0
总计 | 0 | 0.3 | 1.3

## 钓场鱼品质列表
鱼种 | 品质 | 钓场 | 等阶 | 随机权重 | 最小长度 | 最大长度
Tench | _Common | 1 | 3 | 378
Tench | _Trophy | 1 | 3 | 189
Tench | _Unique | 1 | 3 | 94
Tench | _Apex | 1 | 3 | 37
Golden_Bream | _Common | 1 | 4 | 378
Golden_Bream | _Trophy | 1 | 4 | 189
Golden_Bream | _Unique | 1 | 4 | 94
Golden_Bream | _Apex | 1 | 4 | 37
Green_Sunfish | _Common | 1 | 3 | 857
Green_Sunfish | _Trophy | 1 | 3 | 428
Green_Sunfish | _Unique | 1 | 3 | 214
Black_Crappie | _Young | 1 | 2 | 500
Black_Crappie | _Common | 1 | 2 | 500
White_Crappie | _Young | 1 | 2 | 500
White_Crappie | _Common | 1 | 2 | 500
Redspotted_Sunfish | _Young | 1 | 2 | 500
Redspotted_Sunfish | _Common | 1 | 2 | 500
Largemouth_Bass | _Young | 1 | 2 | 500
Largemouth_Bass | _Common | 1 | 2 | 500
Channel_Catfish | _Young | 1 | 2 | 500
Channel_Catfish | _Common | 1 | 2 | 500
Pumpkinseed_Sunfish | _Young | 1 | 1 | 500
Pumpkinseed_Sunfish | _Common | 1 | 1 | 500
Buffalofish | _Young | 1 | 1 | 500
Buffalofish | _Common | 1 | 1 | 500
Redear_Sunfish | _Young | 1 | 1 | 500
Redear_Sunfish | _Common | 1 | 1 | 500
Bluegill_Sunfish | _Young | 1 | 1 | 500
Bluegill_Sunfish | _Common | 1 | 1 | 500
White_Channel_Catfish | _Common | 2 | 5 | 540
White_Channel_Catfish | _Trophy | 2 | 5 | 270
White_Channel_Catfish | _Unique | 2 | 5 | 135
White_Channel_Catfish | _Apex | 2 | 5 | 54
Striped_Bass | _Common | 2 | 5 | 378
Striped_Bass | _Trophy | 2 | 5 | 189
Striped_Bass | _Unique | 2 | 5 | 94
Striped_Bass | _Apex | 2 | 5 | 37
Walleye | _Common | 2 | 4 | 800
Walleye | _Trophy | 2 | 4 | 400
Walleye | _Unique | 2 | 4 | 200
Muskellunge | _Young | 2 | 3 | 500
Muskellunge | _Common | 2 | 3 | 500
Bowfin | _Young | 2 | 2 | 500
Bowfin | _Common | 2 | 2 | 500
Channel_Catfish | _Young | 2 | 2 | 500
Channel_Catfish | _Common | 2 | 2 | 500
Largemouth_Bass | _Young | 2 | 2 | 500
Largemouth_Bass | _Common | 2 | 2 | 500
Black_Crappie | _Young | 2 | 2 | 500
Black_Crappie | _Common | 2 | 2 | 500
Yellow_Perch | _Young | 2 | 2 | 500
Yellow_Perch | _Common | 2 | 2 | 500
Rock_Bass | _Young | 2 | 2 | 500
Rock_Bass | _Common | 2 | 2 | 500